## Cover Page
CP-317-F
Airline Flight Reservation System
Group 15
Product Owner (Developer): Aryan Shah
Scrum Master (Developer): Shazaib Malik
Frontend Lead Developer: Noah Yamin
Backend Lead Developer: Abdullah Mumtaz
Database Engineer (Developer): Mustafa Khan
UI/UX Designer (Developer): Varun Saini
QA/Test Engineer (Developer): Nowaisir Alam
DevOps Engineer (Developer): Ojas Chindarkar
Full-Stack Developer: Qazi Zayad

## Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points | Priority | Sprint | Status | Conversation | Confirmation
UI-01 | Search Flights | As a user, I want to search for flights by entering my travel dates, destinations, and preferences so that I can find available travel options that match my schedule and budget. | 5 | High | Sprint 1 |  | What are the layover and direct flight options displayed | The user is able to search flights with details
UI-02 | View Flight Details | As a user, I want to view detailed information about each flight — including price, duration, layovers, and airline — so that I can compare options before booking. | 5 | High | Sprint 1 |  | How much Information should be displayed to the user | The user is able to see the specefic flight details
RES-01 | Book Flight | As a user, I want to book a flight by selecting my preferred option and entering my personal information so that I can reserve a seat. | 3 | High | Sprint 1 |  | What to do if the perfered option is no longer available | The user is able to succesfully enter information and reserve a seat
RES-02 | Cancel Reservation | As a user, I want to cancel my reservation through my account so that I can change my travel plans without needing to contact support. | 3 | Medium | Sprint 1 |  | Ensure the user gets a verification of cancelation | The user is able to cancel and receive a verification
ACC-01 | User Login | As a user, I want to securely log into my account using my email and password (or other authentication methods) so that I can manage my bookings. | 3 | HIgh | Sprint 1 |  | User creation should use 2 step verification for security purposes | The user is bale to log in and create an account
ACC-02 | View Booking History | As a user, I want to see a list of my past bookings with details such as dates, destinations, and airlines so that I can track my travel history. | 5 | Medium | Sprint 2 |  | How much Information should be displayed to the user | The User is able to see pasy bookings
ADM-01 | Manage Flights | As an admin, I want to add new flights or update existing flight schedules, prices, and availability so that users always see accurate and up‑to‑date information. | 5 | High | Sprint 2 |  | Ensure all information is accurate to local user | The admin is able to add or update flights
ADM-02 | View Passenger List | As an admin, I want to view passenger lists for each flight so that I can manage flight occupancy and ensure compliance with airline requirements. | 5 | High | Sprint 2 |  | Ensure that the passenger information I mostly private | The admin is able to view the passenger list for a specefic flight
REP-01 | Generate Reports | As an admin, I want to generate reports on bookings, revenue, and travel trends so that I can analyze performance and make informed business decisions. | 8 | Medium | Sprint 3 |  | Reports should be exportable to Excel | The admin is able to genereate a report that can be exportable
SEC-01 | Secure Payments | As a user, I want secure and encrypted payment processing so that my financial data is protected during transactions. | 8 | High | Sprint 3 |  | Need to implement secure payment system | The user is able to securly make a payment